## Sheet1
|  | Tasks | Due Date | Owner | Status
2024-02-01 | Start - Form Team / Identify tasks | Create repository and branches | 2024-02-02 | Kenway | Done
|  | Create local repositories | 2024-02-02 | All | In Progress
2024-02-05 | Pulling and Merging with GIT | Create jupiter notebooks (analysis / plotting) | 2024-02-05
Add cells for each activity
2024-02-07 | Hypothesis Testing and Statistical Tests | Add owners to each cell
|  | Analysis: | 2024-02-07
2024-02-08 | Work Day + Install PostgreSQL | Load data - health csv |  | Ipsita | In Progress
Load data - census.gov
2024-02-12 | Work Day | Create dataframes |  |  | In Progress
|  | Questsions 1-3 |  | Ipsita
2024-02-14 | Presentation / Submission | Questions 4-6 |  | Tim
|  | Questions 7-8 |  | Kenway
|  | Clean data |  | All | In Progress
|  | Perform analysis per question (8?) |  | All | In Progress
|  | Export data |  | TBD
|  | Plotting: | 2024-02-09
Import data
Create plots per question
Exports pngs
|  | Report: | 2024-02-12
Create presentation (powerpoint?)
Write analysis of questions
Add plots
Identify talking points/owners
|  | Update Readme: | 2024-02-13
Project details
Links/References